## Open Tickets
MLB Baseball Simulation Platform — Open Ticket Backlog
NEXT FREE TICKET ID: SIM-625
Priority | Ticket ID | Title | Description | Definition of Done | Proposed Solution
P1 | SIM-548 | Fit the draw weights against the betting-line accuracy comparison, the strikeout market first | None of the simulator's similarity weights was chosen to make its predictions more accurate against real results; each was fitted to reproduce the play pool's own frequencies and then checked on the pool-totals bands. The betting-line accuracy comparison (the judge since 2026-09-12) shows where that leaves the model: on the starter strikeout market its probability of clearing the line carries no information (when it says 16% the over happens 56% of the time; when it says 88%, 46%) and scores worse than a coin flip, because the projected strikeouts per start correlate +0.07 with the real count and +0.05 with the pitcher's own strikeout rate (the closing line: +0.45). The pitcher's weight in the pitch draw is nearly flat at its fitted power of 1, so every starter draws a league-average mix. Hits and total bases, by contrast, carry real skill and trail the line by a fraction of a point with a 4-point upward bias. | First, the 1,000-game accuracy baseline and the calibration layer run again on the one-book odds rows of SIM-555 (owner ruling 2026-10-01), and every later read compares against that baseline. The pitcher's weight in the pitch draw has a value chosen by the paired accuracy comparison on 250 games of 2024 and confirmed on 250 games of 2025 it never saw, and production runs it: the strikeout market's paired Brier difference against the 2026-09-13 production is negative beyond its confidence range on both seasons, no other market is worse beyond its range on both, and the discrimination read (the correlation of projected with real strikeouts) is recorded. The same procedure for the batter's weights on the hit markets. Each landed value cites the read that chose it; the lane's flags match the compose file; the runbook carries the procedure. A read that says a weight cannot reach the market is a valid end for that weight, recorded with the number. | FROM THE ODDS RE-LOAD (SIM-555, owner ruling 2026-10-01): the full re-run of the 1,000-game baseline (about 16 hours, the app stopped; scripts/accuracy_baseline_1000.sh plus the first 250 games of scripts/accuracy_split_arm.sh) and the calibration layer's refit (scripts/calibrate_markets.py) run inside this ticket, on the one-book odds rows. Until then only the fixed-line markets are re-priced (docs/audit/records/sim548_baseline_1000_skill.sim555.txt); the totals, run lines, team totals, first-five markets and props keep the old consensus lines, and the graded line moved on 15-35% of those records. FROM THE FENCE CERTIFICATION (SIM-478/479/480, 2026-09-22): the born batted ball's kernel over-produces doubles on ORDINARY air balls - balls 60+ ft short of the fence draw an extra-base hit 11-13% of the time against the pool's 9-10%, and the 45x130 lane reads doubles per ball in play +5.8% (accepted by the owner, 2026-09-22). The near-wall balls now read right (the class ruler, the exponent per feature and the wall-margin band). The lever is the kernel's bandwidth and its density correction on ordinary air balls - a weight, so this sweep owns it. STATUS 2026-09-16 (04:42 UTC): PAUSED by owner decision - the fit runs once the model is in its final state; the owner works on other tickets first. The four-factor design on the full simulator stopped at run 3 of 21 (runs 1-2 kept in results/sim548/sim548_design_20260915/); the offline fit v2 READ (per pitch flat wins, between pitchers sharp wins, per start flat within noise - the design decides); everything committed (5f6a0ef). The resume order is in docs/audit/2026-09-14-sim548-joint-fit-plan.md s11: the pool-window test first (does a ten-season pool cure the sharp draw's starvation; do old rows predict worse at equal similarity; the recency decay is an unfitted weight), then the design on the chosen pool, then the 2025 hold-out, the flip, the calibration layer. Any change to the pool, the bundle, the profiles or the draw code before the resume invalidates the two finished runs (expected). STATUS 2026-09-15 (06:30 UTC): PLAN v2 IN EXECUTION (owner: 'implement your plan'). Built: the skill table, the calibration layer (scripts/calibrate_markets.py), the offline joint fit for the pitch draws (scripts/offline_draw_fit.py), the designed-experiment runner (scripts/designed_experiment.py); 11 unit tests. First calibration read on held-out 2024 games: the strikeout map (b 0.15) brings the market LEVEL with the line; batter props pass. The offline fit (78 settings) and the pool-totals lane on today's production are running. The Docker VM is now 16 CPU / 19.5 GiB. STATUS 2026-09-15: the 1,000-game baseline of production READ (docs/audit/records/sim548_baseline_1000_skill.txt; CHANGES.md 2026-09-15). Worst market: strikeouts (+0.022 Brier behind the line) - but the sim's discrimination now equals the line's (AUC 0.55 vs 0.54); the gap is a 9.5-point low bias and a 3x over-spread = calibration-layer work. The moneyline's gap (+0.011) is a stale win-probability curve in /data/calibration.json that maps raw 0.545-0.618 to 0.500 (owner decision: retire it now or refit on raw probabilities). The run level is real: totals over-predicted by 4.6-5.3 points; the batter excess sits in the weak third of hitters (the batter weight too flat). STATUS 2026-09-14 (evening): the split FLIPPED ON in production by owner decision (16 / 16 / 8; no 2025 hold-out); the 1,000-game accuracy baseline of the flipped production RUNNING (games 251-1000 of 2024 in three chunks, scripts/accuracy_baseline_1000.sh; the first 250 = results/sim548/sim548_accuracy_split.json), done ~04:40 UTC 2026-09-15; the per-market skill table (scripts/market_skill.py) reads it. STATUS 2026-09-14 (later): plan v2 DRAFTED for the owner's review - docs/audit/2026-09-14-sim548-joint-fit-plan.md (one model; a composite objective over every market; an offline joint fit of every draw's weights; a ~20-arm designed experiment on the full simulator; the 2025 hold-out; a per-market calibration layer; no per-market weight sets). Eight owner decisions listed in its section 9. STATUS 2026-09-14: Part A4 RAN - the pitch / pitch-result split (16 / 16 / 8) as a paired accuracy arm over production with the fatigue weight at 0.5: starter strikeouts -0.0155 Brier [-0.0258, -0.0050] (the gap to the closing line halved; AUC 0.51 -> 0.55, the line 0.58; a 6.5-point LOW bias), the moneyline -0.0050 (AUC 0.49 -> 0.58), batter props flat; one guard worse beyond its range (the first-five total +0.0113, whose baseline row is the outlier of four reports). NEXT: Part C, the 2025 hold-out (a production baseline + a split arm on 250 games of 2025; ~6.5 h); the split flips if the strikeout sign holds and no guard worsens on both seasons. The owner asked whether a one-weight-at-a-time ladder can miss interactions between weights (it can: one concentration budget, both actors on the same outcome, the chain from the pitch draw to the result draw); the answer proposes a return pass, a 3x3 grid on the pitcher / batter pair, and an offline joint fit on real held-out pitches before the full-game confirmations - to be written into the plan on the owner's word. Follow docs/audit/2026-09-14-sim548-accuracy-fit-plan.md. Per weight: (1) the 35-minute probe screen (does it move a market probability at all, and the new discrimination read); (2) a ladder of values, each a 2.5-hour paired arm of scripts/accuracy_comparison.py on the fixed 250-game 2024 list against the production baseline, read with scripts/pair_accuracy.py and the new per-market skill table; (3) the choice: the best strikeout-market improvement, the smallest power among ties, every other market not worse; (4) the 2025 hold-out; (5) the flip. First cycle: SIM_PITCH_PITCHER_POWER over 1/2/4/8/16 plus the built pitch/pitch-result split at 16/16/8; if the pitcher score carries no strikeout information at any power, add a results similarity (the pitcher's own strikeout and walk rates against the row pitcher's) as one more draw weight and ladder that. Second cycle: the batter powers on the hit markets. About two days of compute per cycle on the current 6-CPU Docker VM.
P2 | SIM-575 | Read each manager's profile in the API's runs, so the steal draw's manager weight is not flat | The steal draw weighs each row by the batting manager's measured steal rate over the league mean. The API's runs (/simulate, the projections and the what-if) never read the manager profiles. build_sim_kwargs passes con=_get_sim_duckdb(request), and nothing sets app.state.sim_duckdb since the replay store moved to app.state.replay_duckdb. So resolve_manager_profiles_onto_state(state, None) returns at once, the kwargs carry manager_profiles == {0: {}, 1: {}}, and the manager weight reads 1.0 for every team. scripts/sim_stats.py and the accuracy comparison do read the profiles, so the lanes and the users run different simulators. Found by the code clean-up (SIM-493, B1 simulation, 2026-10-20); the evidence is in its CHANGES.md entry. | An API run's kwargs carry each side's manager profile and the season's manager league means. A unit test builds the API's kwargs with no DuckDB connection on app.state and finds both. | Read the profiles through open_sim_duckdb(), as the park-factor snapshot does, or load them into the boot snapshot and read them from there.
P2 | SIM-576 | Write the catcher engine's feature names in the catcher's league-average row | The profile computor writes the catcher row of derived.league_averages with the keys framing_runs, blocking_runs and cs_rate. The catcher engine reads its eleven feature names with pj.get(f, 0.0) or 0.0, and only cs_rate matches. So the shrinkage pulls ten features toward 0.0: a constructed 300-pitch catcher reads pop time 1.95 -> 1.857 s and arm strength 81 -> 77.1 mph. The error reaches the catcher and catcher_throwing score matrices, which weight the steal and pickoff draws. Found by the code clean-up (SIM-493, B4 similarity and betting, 2026-10-20); the evidence is in its CHANGES.md entry. | The catcher's league row carries every engine feature. A missing key reads as NaN, as the steal engines do. The nightly matrices are rebuilt. | In pipeline/batch/profiles (the catcher league row), write the engine's eleven feature keys. In similarity/engines/catcher_similarity.py _load_league_averages, read a missing key as NaN.
P2 | SIM-577 | Write all thirteen features in the extra-base runner's league-average row | The baserunner row of derived.league_averages holds extra_base_attempt_rate, extra_base_success_rate, sb_success_rate, sprint_speed and the Savant rate. The engine reads thirteen features, so the four per-situation attempt rates, stop_rate and the four per-situation success rates shrink toward 0.0. The matrix build loads the thin profiles, so the effect is large there: a 5-chance runner's first-to-third attempt rate reads 0.35 -> 0.088. The error reaches the runner_adv matrix, which weights the advancement draws. Found by the code clean-up (SIM-493, B4 similarity and betting, 2026-10-20); the evidence is in its CHANGES.md entry. | The runner's league row carries every engine feature, and a missing key reads as NaN. The nightly matrices are rebuilt. | Write the engine's thirteen feature keys in the computor's baserunner league row; read a missing key as NaN in similarity/engines/baserunner_similarity.py.
P2 | SIM-578 | Load a database NULL as NaN, not 0.0, in the baserunner, catcher, batter and manager engines | The _v helpers of four engines read v or 0.0. A runner with no Savant row gets sprint speed 0 ft/s (still 20 ft/s after a 5-chance shrink, many deviations below the league's 27), so his speed score is about 0 against every measured runner. A runner who never tried reads 0% success; a NULL arm strength reads 0 mph; a manager-season with no bullpen-availability rows reads available_reliever_usage_rate near 0. The two steal engines already load NaN (the running-game work, SIM-531). Found by the code clean-up (SIM-493, B4 similarity and betting, 2026-10-20); the evidence is in its CHANGES.md entry. | Each of the four engines loads NULL as NaN, and its kernel or shrink handles a NaN feature. The nightly matrices are rebuilt. | Map None to NaN in each _v helper and add the features to each engine's NaN set, as the steal engines do.
P2 | SIM-579 | Select the pitcher's zone-take rate before the chase rate, so the two stay in feature order | In similarity/engines/pitcher_similarity.py _load_profiles, the SELECT returns chase_rate, zone_take_rate and the unpack names them zone_take_rate, chase_rate. So command_vec holds them in the opposite order to COMMAND_FEATURES and the league-average vector, and the shrinkage pulls each pitcher's chase rate toward the league's zone-take rate (weight 1 - alpha, at most 2.4% at 200 pitches). The kernel itself ignores the order. The error reaches the pitcher similarity matrix. Found by the code clean-up (SIM-493, B4 similarity and betting, 2026-10-20); the evidence is in its CHANGES.md entry. | The SELECT order matches COMMAND_FEATURES, and a unit test pins it. The nightly matrices are rebuilt. | Select zone_take_rate before chase_rate.
P2 | SIM-580 | Make the pitcher arsenal fit reproducible: order the pitch rows before the mixture fit | The pitch-vector query in _compute_pitcher_profiles (pipeline/batch/profiles/pitcher.py) has no ORDER BY. DuckDB's parallel Postgres scan returns the rows in a different order on every read, and the seeded mixture fit (random_state=42) depends on the row order. So every profile rebuild gives a different arsenal for nearly every pitcher (a different number of components for about one pitcher in five), and with it a different pitcher similarity matrix. Found by the code clean-up (SIM-493, B2 pipeline, 2026-10-20); the evidence is in its CHANGES.md entry. | Two profile builds of the same code from the same data write the same arsenals, by content. | Add ORDER BY game_pk, at_bat_number, pitch_number to the query. It changes every arsenal once.
P2 | SIM-581 | Name only real tests in the nightly acceptance lane's required roster | The REQUIRED roster of .github/workflows/acceptance-nightly.yml lists test_full_pool_out_advancement_runs_sim450, test_full_pool_steal_decision_runs_sim450 and test_reach_on_error_band_sim450. No test of those names exists, and the roster step fails when a required name did not run. So the nightly lane reds on every run, whatever the bands read. Found by the code clean-up (SIM-493, B5 scripts and test harness, 2026-10-20); the evidence is in its CHANGES.md entry. | The roster names only real tests, and one nightly run passes its roster step. | Delete the three names, or name the tests that took their place.
P2 | SIM-582 | Add last_seen_at to the two odds archive tables, so the retirement copy fits again | Migration 0029 added last_seen_at to raw.game_odds and raw.prop_odds and not to their archives (raw.game_odds_archive, raw.prop_odds_archive, migration 0028). The retirement script copies rows with INSERT ... SELECT *, which needs the same columns in the same order, so the next retirement fails. The integration test test_schema_migrations.py::test_sim555_stamp_indexes_and_archives reds on master fe81d79 and on the clean-up branch for this reason. Found by the code clean-up (SIM-493, the integration pass, 2026-10-20); the evidence is in its CHANGES.md entry. | Both archives carry last_seen_at in the live table's position, the integration test passes, and a retirement run copies a row. | A new Alembic migration adds last_seen_at to both archives (nullable, so the copied rows keep their value), placed after book_line_at to match the live tables; check the column order with the test.
P2 | SIM-583 | Keep the calibrated win probability strictly between 0 and 1 | build_validation_report fits the reliability curve with min_bin_count=1, so a bin of two games can map 0.75 to 1.0. Example: the curve [[0,0],[0.45,0.44],[0.55,0.56],[0.73,1.0],[1,1]] and home_win_pct 0.75 at n = 100 give home 1.0, away 0.0 and an interval of zero width. Found by the code clean-up (SIM-493, B1 simulation, 2026-10-20); the evidence is in its CHANGES.md entry. | No calibrated probability is 0.0 or 1.0, and a unit test feeds the curve above. | Fit the curve with a min_bin_count near 30, or clamp the mapped probability to [eps, 1 - eps].
P2 | SIM-584 | Stamp the accuracy report with the bundle the run read, not the live link | scripts/accuracy/selection.py bundle_provenance reads the manifest times under BASEBALL_PLAY_POOL_DIR/engine_artifacts (the live link). The factory reads BASEBALL_ENGINE_ARTIFACT_DIR when it is set (simulation/production_factory.py). Seen on 2026-10-20: two runs on the same pinned bundle, before and after the nightly rebuild, carry different manifest_mtimes and identical records, so pair_accuracy.py refuses to pair them; two runs on different pinned bundles on one day would pair. The weight fit (SIM-548) pairs these reports. Found by the code clean-up (SIM-493, B5 scripts and test harness, 2026-10-20); the evidence is in its CHANGES.md entry. | The stamp names the bundle the run read, and a test pins the pinned-directory case. | Read the pinned directory first, as the factory does.
P3 | SIM-547 | Manager-draw follow-ons: the pen on the API, the preview-game fallbacks, the pen order and a finer rest fit | The pitching change now follows each team's real manager and real bullpen (flipped on 2026-09-13). Five small gaps remain. The game-state API response does not show the pen or where it came from. A game that has not started yet has no manager id and no bullpen listing, so the simulator treats it as an average manager with an invented pen. The pen lists the relievers who sat out today at the back, which the fallback pick reads as 'the closer is first'. The entering arm pitched yesterday 27% of the time against 16.5% in the real data, and its early-inning role reads 0.37 against 0.31. | The API's live game state carries each side's pen and its source (box or synthetic). A preview game takes the team's most recent Final game's manager and its most recent listing with a staleness flag. The pen order no longer encodes who sat out today. A rest bandwidth of 0.25 days is measured with the manager probe and adopted if it brings the entering arm's 'pitched yesterday' share within 5 points of the pool's without breaking the other reliever reads. | Expose ResolvedLineup.bullpen / bullpen_source on LiveGameStateResponse (api/routes/games.py, api/schemas.py). In simulation/lineup_resolver.py, fall back to the team's latest Final game for the manager id (raw.games) and the listing (raw.game_bullpen) when the game's own are missing, and flag the staleness in bullpen_source. In pipeline/bullpen_usage.pen_from_listing, order the pen by the listing's own order (or by rest) instead of pitched-first. Run scripts/probes/manager_probe.py with rest=0.25 (and 0.35) against the r_base / r_rest05 arms and read the reliever line.
P3 | SIM-526 | Turn on the catcher pitch-receiving factor | The team built a feature that scores how good each catcher is at making a borderline pitch look like a strike (sometimes called 'framing'), which can affect whether a close pitch is called a ball or a strike. It is built and tested but currently switched off in the live simulator, pending a decision on how strongly to weight it. | The catcher pitch-receiving factor has a chosen strength setting and is switched on in production without breaking any of the platform's existing accuracy checks. | Decide the weight to give this factor based on testing already done, turn it on, and confirm the standard accuracy checks still pass.
P3 | SIM-556 | Keep the number of steal attempts right when the steal draw weighs rows by how much their players resemble the live ones (the balance weight) | The simulator decides a steal by drawing one real past pitch from a pool. It weighs each candidate row by how much its runner, pitcher and catcher resemble the players in the game (the look-alike weights). Those weights lower the number of steal attempts. Base stealers are rare and resemble few other runners, so their rows are drawn less often than their share of the pool, and those rows hold most of the attempts. On a replay of 74,296 real pitches of 2026 the draw reads 1.225 steals per 100 chances against 1.462 in the pool (16% low); 2025 reads 14% low. The runner weight carries three quarters of the loss, the pitcher weight a fifth, the catcher weight the rest. This matches the two red steal-attempt bands of the acceptance lanes of 2026-09-21 and 2026-09-22 (-9.1% at second base, -17.9% at third). The draw's bell curve on the score margin has the same flaw the other way and adds 4%. A stronger weight alone does not repair it: at strengths 4 / 4 / 2 the total is 22% low, and at 12 / 12 / 2 it is 8.5% low with much worse odds per pitch. It is not the rows with no score and not the engines' sample-confidence multiplier (each moves the total by under half a point). Finding and evidence: docs/audit/2026-09-30-steal-weight-volume-finding.md and scripts/probes/steal_weight_volume_probe.py with its records (docs/audit/records/steal_weight_volume_probe_2025.* and _2026.*; the arrays in results/steal_weight_volume/). Filed P3 by the owner on 2026-10-01. | The steal draw carries a balance weight on its three look-alike weights and on the score-margin curve, switched on in production. The pool replayed through each weight alone keeps between 0.98 and 1.02 of the pool's steal attempts, and the nightly matrix build prints that check. On the replay of real pitches the draw reads within 1% of the pool's rate at every strength tried (1 / 1 / 1, 4 / 4 / 2, 12 / 12 / 2), and the per-runner match between expected and real steals does not fall (0.710 today on 2026, 0.743 with the fix on the replay). One 45 x 130 acceptance lane reads the two steal-attempt bands inside their floors and the safe-share band still green. The owner has a recommendation on the strength of the runner weight in the steal draw: with the balance, 4 / 4 / 2 is the best row tested (base stealers 2.36 per 100 against a real 3.02; 1.78 at strength 1). | In simulation/full_pool_sampler.py, add one number per player-season to the steal draw's weight (the balance weight). Fit it when the sampler loads, from the score matrix and the pool's row counts only (it never reads the attempted flag), by the alternating rescale (Sinkhorn): each player's rows must receive, over a season of draws, the share of the draw they hold. Fit it with only the simulated season's player-seasons as the live players and over the rows that season can draw (fitted on the whole pool it reads 5% low on 2026). Multiply it in _steal_actor_factor; cap it at 20; give a row with no score the mean scored weight at every power. Fit the same balance on the score-margin curve inside each count cell (eleven weights). One switch, SIM_STEAL_BALANCE, landing on with the cheap gates (the unit and regression lanes, a ten-game smoke of the steal channels), then the lane. Early in a season, add the season before to the live set (threshold not tested). Second step: run the same pool-replay check on the look-alike weights of the other draws (pitch, fielding, advancement, pitching change); the lane's red walks (+4.0%) and hit-by-pitch (+6.7%) bands are untested candidates. Reference fit: balance_weight_live in scripts/probes/steal_weight_volume_probe.py; the design is section 3 of the finding.
P3 | SIM-574 | Make each SIM_* flag's code default equal its production value, or record why it differs | The simulator reads its switches and weights from SIM_* environment flags. Each flag has a default in the code (the value an unset flag reads) and a production value set in the app service of docker-compose.yml. They differ for 24 of the flags compose sets (measured 2026-10-20): for example the pitch-draw cell index is off in code and on in production, and the fence stage, the fielding class filter and the manager draw are the same. So a script, a probe or a test that forgets one flag runs a different simulator from production, silently. The registry of the flags (simulation/flags.py, the code clean-up SIM-493) now lists every default in one table, which makes the gap visible but does not close it. | For every registered flag the code default equals the compose value, or the registry row says in one line why it differs (for example: the unit lane's byte-identical state). The unit lane's own pins in tests/conftest.py still hold its state. The fingerprint (scripts/behaviour_fingerprint.py) of production is unchanged, because compose already sets the production values. | Owner decision first: should an unset flag mean production or off? If production: change each default in simulation/flags.py to the compose value, keep tests/conftest.py's pins for the unit lane, and add a registry test that the defaults equal compose. If off: add the reason column to the registry and a test that compose sets every flag whose default differs.
P3 | SIM-585 | Refuse CORS_ORIGINS=* while the API sends credentials | api/main.py sets allow_credentials=True for every origin list, and resolve_cors_origins (api/auth.py) returns ['*'] when an operator sets CORS_ORIGINS=*. Starlette then echoes the caller's Origin on a request with a cookie, so any site can read the API with the user's login. Production sets neither variable today, so the defect is latent. Found by the code clean-up (SIM-493, B3 API and frontend, 2026-10-20); the evidence is in its CHANGES.md entry. | CORS_ORIGINS=* either fails the boot or turns credentials off, and a unit test pins it. | Refuse '*' in resolve_cors_origins while credentials are on.
P3 | SIM-586 | Ask the schedule only for game types raw.games accepts | GAME_TYPES (pipeline/live/ingestion/constants.py) is R F D L W C P; the CHECK on raw.games allows R P S A D F L W. A game of type C on the slate fails its upsert. Found by the code clean-up (SIM-493, B2 pipeline, 2026-10-20); the evidence is in its CHANGES.md entry. | The live pipeline's game types and the table's CHECK agree, and a unit test compares them. | Drop C from GAME_TYPES, or widen the CHECK with a migration if type C games should load.
P3 | SIM-587 | Decide which calibration values the draws use, and make the code follow | similarity/calibration/pitcher.py fits sigma_command and eb_n_prior_pitcher, and no code reads either, so the pitcher engine keeps RBF_SIGMA_COMMAND 1.0453 and EB_N_PRIOR 5. More broadly, the nightly actor matrices apply no calibration report (build_actor_sim_matrices): make calibrate changes only the API's engines. Found by the code clean-up (SIM-493, B4 similarity and betting, 2026-10-20); the evidence is in its CHANGES.md entry. | The owner decides which values the draws use, and the code and the docs follow. | Read both fields in apply_calibration and apply /data/calibration.json in the matrix build; or document the module defaults as the draws' values.
P3 | SIM-588 | Compute the z of the requested level in GameSimSummary.from_results | GameSimSummary.from_results(confidence_level=0.85) computes the 95% z and labels the intervals 0.85. Found by the code clean-up (SIM-493, B1 simulation, 2026-10-20); the evidence is in its CHANGES.md entry. | Each level gets its own z, and a unit test checks 0.85. | Use NormalDist().inv_cdf((1 + level) / 2), or raise on a level outside the table.
P3 | SIM-589 | Treat both samples as samples in the replay chi-squared test | The two-sample path of replay_chi_squared.chi_squared_gof treats the reference sample as exact. Two independent samples of 1,000 Poisson(4.4) totals were rejected 52.5% of the time at alpha 0.05 over 400 trials. replay_and_test uses it. Found by the code clean-up (SIM-493, B1 simulation, 2026-10-20); the evidence is in its CHANGES.md entry. | Two samples from one distribution are rejected near alpha. | Use scipy.stats.chi2_contingency on the pooled 2 x k table.
P3 | SIM-590 | Compare the historical replay against the right side's score | replay_historical_games always compares the simulated HOME score. A HistoricalGame row does not say which side its runs belong to, so an away team's runs meet the simulated home runs. Found by the code clean-up (SIM-493, B1 simulation, 2026-10-20); the evidence is in its CHANGES.md entry. | A HistoricalGame row names its side, and the replay compares like with like. | Add a side field to HistoricalGame.
P3 | SIM-591 | Charge the losing pitcher with the go-ahead run, as MLB does | pitcher_decisions charges the pitcher on the mound at the decisive play. In a tie, A walks a batter, B relieves him and allows a double that scores the runner, and the lead holds: MLB charges A; the simulator charges B. Found by the code clean-up (SIM-493, B1 simulation, 2026-10-20); the evidence is in its CHANGES.md entry. | The decision follows the runner's responsible pitcher, and a unit test plays the example. | Carry each runner's responsible pitcher on the bases.
P3 | SIM-592 | Put the batter on first after a forced reach with no batter id | _force_on_reach with no batter id leaves first base's runner on first after pushing him to second (b.first = state.batter_id if ... else b.first), so the base check raises; _resolve_walk assigns b.first = state.batter_id for the same case. Reachable only with a sampler and no lineup. Found by the code clean-up (SIM-493, B1 simulation, 2026-10-20); the evidence is in its CHANGES.md entry. | The forced reach and the walk give the same bases. | Use the walk's assignment.
P3 | SIM-593 | Void the plate appearance after a third out on the bases in the single pre-pitch steal draw | With SIM_STEAL_PITCH_CLASS=0 (not production), a pickoff or a caught stealing that makes the third out before the pitch's result still ends the plate appearance, so the pitcher gets a batter faced and the batter an at-bat. Found by the code clean-up (SIM-493, B1 simulation, 2026-10-20); the evidence is in its CHANGES.md entry. | The single draw voids the plate appearance as the running game on the pitch does. | Apply the no-pitch void of the class-aware draw.
P3 | SIM-594 | Let the batter run on a called third strike that gets away | Rule 5.05(a)(2) lets the batter run on any uncaught third strike. _dropped_third_strike reads swinging strikes only. Two such rows exist in 2023-2026, both in 2026. Found by the code clean-up (SIM-493, B1 simulation, 2026-10-20); the evidence is in its CHANGES.md entry. | A called third strike that gets away can be a dropped-third-strike reach. | Let _dropped_third_strike read a called third strike too.
P3 | SIM-595 | Fix the article in the what-if's ineligible-player message | whatif.apply_changes' message for an ineligible pinch hitter reads 'is not an bench hitter'. Found by the code clean-up (SIM-493, B1 simulation, 2026-10-20); the evidence is in its CHANGES.md entry. | Each label reads with its own article. | Put the article inside each label.
P3 | SIM-596 | Decide what the what-if does when the designated hitter takes the field | A designated hitter moved to the field leaves the fielder he replaced in the batting order with no position. The rule that ends the designated hitter is not modelled in simulation/whatif.py. Found by the code clean-up (SIM-493, B1 simulation, 2026-10-20); the evidence is in its CHANGES.md entry. | The owner decides whether the what-if models the rule, and the code follows. | Model the rule: the pitcher bats in the replaced fielder's slot, or refuse the change.
P3 | SIM-597 | Write the pitching-change pool's role file in a fixed row order | roles.parquet (build_pitching_change_pool, pipeline/batch/artifacts/manager_pool.py) is written from a GROUP BY with no ORDER BY, so two builds of the same code from the same data write its rows in a different order. No reader uses the order, but the fingerprint's bundle mode reads a difference on every build. Found by the code clean-up (SIM-493, B2 pipeline, 2026-10-20); the evidence is in its CHANGES.md entry. | Two builds give the same file, by content. | Add ORDER BY pitcher_id, season. It changes no game.
P3 | SIM-598 | Read the runners under the names the live service sends | frontend/src/hooks/useGameSocket.ts reads runner_on_first / _second / _third; the live service sends on_1b / on_2b / on_3b. The hook's on_1b to on_3b are always undefined. No page reads them today. Found by the code clean-up (SIM-493, B3 API and frontend, 2026-10-20); the evidence is in its CHANGES.md entry. | A game_state_update with runners fills the hook's on_1b to on_3b. | Read gs.on_1b, gs.on_2b and gs.on_3b in mapWsState.
P3 | SIM-599 | Describe the slate card's odds field as it is | The route description (api/routes/games_slate.py) and the model (api/routes/games_models.py) call the field 'reserved for the Phase-6 odds-provider integration (SIM-405)'. The field is always None: the card's lines come from /api/betting/games/{pk}/card-odds. Found by the code clean-up (SIM-493, B3 API and frontend, 2026-10-20); the evidence is in its CHANGES.md entry. | Both texts say that, with a fresh API snapshot (CLAUDE.md section 15). | Rewrite both texts; run scripts/export_openapi.py in the image and npm run gen:api.
P3 | SIM-600 | Name the current state in the API's version and health strings | api/main.py carries the app version 0.1.0-phase7, "phase": "6" on /health and "6 - Frontend Build (in progress)" on /. Found by the code clean-up (SIM-493, B3 API and frontend, 2026-10-20); the evidence is in its CHANGES.md entry. | The strings name the current state, or go. | Drop the phase keys and set the version from one constant.
P3 | SIM-601 | Make the Playwright smoke tests pass while the live app runs | frontend/e2e/smoke.spec.ts (three specs) fail on the owner's host: a request the test does not mock goes through the preview server's proxy to localhost:8000, the live app answers 401 and the page shows the login. With API_TARGET=http://127.0.0.1:9 all 21 tests pass; CI has no backend, so CI passes. Found by the code clean-up (SIM-493, B3 API and frontend, 2026-10-20); the evidence is in its CHANGES.md entry. | The e2e suite passes with the live app running. | Set API_TARGET to a closed port in playwright.config.ts's webServer.env, or end each spec with a catch-all **/api/** route that answers 404.
P3 | SIM-602 | Make two API tests check what their names say | tests/unit/test_api_betting.py test_clv_snapshot_returns_only_series_with_clv makes a GET and asserts nothing. tests/unit/test_api_games_plays.py test_simulate_ok_without_duckdb_then_plays_404 never requests /plays. Found by the code clean-up (SIM-493, B3 API and frontend, 2026-10-20); the evidence is in its CHANGES.md entry. | Each test asserts what its name says. | Add the assertions (the CLV series' filter; /plays answers 503 with no replay store), then rename the second test.
P3 | SIM-603 | Return the fielder's infield sub-scores in the same order from query_pair as from query | For an infielder, similarity/engines/fielder_similarity.py query_pair returns the specialty score in tertiary_score and the error score in quaternary_score; query returns them the other way round, as the Similarity Explorer's labels expect. Two shortstops with different error rates and equal specialty values: query gives 0.0710 / 1.0000, query_pair 1.0000 / 0.0710. The composite and the matrices are right. Found by the code clean-up (SIM-493, B4 similarity and betting, 2026-10-20); the evidence is in its CHANGES.md entry. | query and query_pair agree on every sub-score, and a unit test compares them. | Map the infield tuple in SimilarityResult order.
P3 | SIM-604 | Apply the per-hand 30-PA platoon rule in the batter engine's pair score | similarity/engines/batter_similarity.py _score_pair disagrees with score_all on a thin platoon split. A query with 30+ PA against either hand turns the platoon weights on for any vs_hand (10 PA vs L and 200 vs R with vs_hand='L': 0.8642 against 0.8900), and a candidate under 30 PA never gets the neutral 0.5. It serves query_pair (the Explorer's pair view and the diagnostics); the matrix is unaffected. Found by the code clean-up (SIM-493, B4 similarity and betting, 2026-10-20); the evidence is in its CHANGES.md entry. | _score_pair and score_all agree, and a unit test compares them. | Use score_all's per-hand rule in _score_pair.
P3 | SIM-605 | Keep one pitcher engine's calibration from rewriting every pitcher engine | PitcherSimilarityEngine.apply_calibration sets the module global ARSENAL_SCALE, and a report with no gamma resets it to 4.10. The API builds two instances. Latent: no production path calls it today. Found by the code clean-up (SIM-493, B4 similarity and betting, 2026-10-20); the evidence is in its CHANGES.md entry. | Each instance carries its own scale. | Pass the instance's scale into the three readers.
P3 | SIM-606 | Pick the small-mixture-component merge target in standardized units | enforce_min_cluster_size runs before the standardization in the arsenal build, so spin rate (hundreds of rpm) decides the merge over velocity and movement. Found by the code clean-up (SIM-493, B4 similarity and betting, 2026-10-20); the evidence is in its CHANGES.md entry. | The merge measures the gap in standardized units. | Measure the gap over the mixture's feature_stds.
P3 | SIM-607 | Read the line-movement direction book by book | betting/line_movement.py _net_direction pools every book, so the first and last quotes can come from two books: (t1, bp:1, -110/-110) and (t2, bp:2, -130/+110) give direction 'toward' and a CLV, though neither book moved. Found by the code clean-up (SIM-493, B4 similarity and betting, 2026-10-20); the evidence is in its CHANGES.md entry. | The direction is each book's own, then aggregated. | Compute the direction per book, then aggregate.
P3 | SIM-608 | Store a price that returns to an earlier value | The odds writer dedups on a hash with no time (ON CONFLICT (game_pk, source, odds_hash)), so -110 at t0, -120 at t1, -110 at t2 closes the series at -120. Read from the code, not checked against stored data. Found by the code clean-up (SIM-493, B4 similarity and betting, 2026-10-20); the evidence is in its CHANGES.md entry. | A return to an earlier price is stored, and the series closes on the last price. | Dedup only against the latest row of the same game, source, book, market and line type.
P3 | SIM-609 | Raise on a wrong market or side in the line-movement series | line_movement_from_quotes swallows _side_columns' ValueError, so a wrong market or side gives a silent empty series. Found by the code clean-up (SIM-493, B4 similarity and betting, 2026-10-20); the evidence is in its CHANGES.md entry. | A wrong market or side raises. | Call _side_columns once before the loop.
P3 | SIM-610 | Similarity and betting: seven small defects | (1) SituationSimilarityEngine.query_batch([]) raises instead of returning []. (2) The engines' and the calibrator's __main__ blocks read a DuckDB path that does not exist (../../db/schemas/baseball_simulator.duckdb); the pitcher engine's block builds and prints nothing. (3) CalibrationReport.summary() prints no row for the batter's physical weights. (4) The Similarity Explorer's batter panel (api/routes/similarity_explorer.py) shows the four-way weights 0.40/0.35/0.15/0.10. (5) A log line in batted_ball_similarity.py says 'until SIM-051 ships'. (6) tests/regression/conftest.py scales the situation fixture's index twice. (7) No writer sets is_sharp_book, so sharp_consensus is always None. Found by the code clean-up (SIM-493, B4 similarity and betting, 2026-10-20); the evidence is in its CHANGES.md entry. | Each of the seven is fixed or retired. | One edit each; retire sharp_consensus if no book will be marked sharp.
P3 | SIM-611 | Owner decisions: four similarity design points | Not defects, design points for the owner. (1) The catcher's shrinkage prior is 15 called pitches, so alpha is at least 0.95 for every kept catcher (framing stabilizes near 1,500). (2) stop_rate is exactly one minus the overall attempt rate, so that rate counts twice in the runner's aggression distance. (3) The batter's xba / xslg and the manager's hit-and-run and double-switch rates read 0.0 for everyone and still hold their share of the kernel weight. (4) CLAUDE.md section 1 calls CLV 'the gold-standard metric'; the owner ruled on 2026-09-28 that the model is not judged by it. Found by the code clean-up (SIM-493, B4 similarity and betting, 2026-10-20); the evidence is in its CHANGES.md entry. | The owner rules on each point, and the code or CLAUDE.md follows. | Raise the catcher prior; drop stop_rate; drop the all-zero features; rewrite CLAUDE.md section 1.
P3 | SIM-612 | Read the pitch rebuild's before-smoke from results/ | scripts/pitch_pool_rebuild/export.py _smoke_games opens scripts/sim553_smoke_before.json; the groundwork moved run outputs to results/sim553/. The function always prints its placeholder. Found by the code clean-up (SIM-493, B5 scripts and test harness, 2026-10-20); the evidence is in its CHANGES.md entry. | It reads the results/ path. | Change the one path.
P3 | SIM-613 | Print n/a in the hypothetical-return table when no bet qualifies | scripts/accuracy/hypothetical_return.py _fmt_row formats the means and the range with :.4f and no guard for None. With no qualifying bet the table raises TypeError, and run() prints it before it writes the report and before the zero-games check, so the run ends in a traceback with no report and no exit code 5. Found by the code clean-up (SIM-493, B5 scripts and test harness, 2026-10-20); the evidence is in its CHANGES.md entry. | The table prints n/a, as the accuracy table does. | Use the _fmt_or_na guard.
P3 | SIM-614 | Retry a sweep attempt that crashes before its first game | scripts/resumable_sweep.py applies its zero-progress stop (gained == 0) after a crash too, so a segfault before the first game of an attempt ends the sweep (exit 1) instead of retrying. Found by reading the code; not exercised. Found by the code clean-up (SIM-493, B5 scripts and test harness, 2026-10-20); the evidence is in its CHANGES.md entry. | A crashed attempt with no gain retries up to --max-attempts. | Apply the stop only to an attempt that exited cleanly.
P3 | SIM-615 | Retire the odds-hash backfill probe | scripts/probes/backfill_odds_hash.py _dedup_rows orders by received_at, a column raw.game_odds does not have, so its DELETE fails; its ODDS_COLUMNS leaves out draw_ml. Both are dormant: the unique index and the NOT NULL hash of migration 0012 ended the probe's job. Found by the code clean-up (SIM-493, B5 scripts and test harness, 2026-10-20); the evidence is in its CHANGES.md entry. | The probe is retired. | Delete the probe and its test.
P3 | SIM-616 | Decide the minimum-sample read's two known limits | scripts/accuracy/confidence.py: the 0.02 floor assumes a coin-flip market, so its power is weaker than stated for a market far from 0.5 (a home-run prop); and a small sample whose observed spread is exactly zero reads as fully resolved. An adversarial review of the minimum-sample work (SIM-539) found both. Found by the code clean-up (SIM-493, B5 scripts and test harness, 2026-10-20); the evidence is in its CHANGES.md entry. | The owner decides whether to fix or accept them. | A per-market 4p(1-p) correction and an upper bound on the spread.
P3 | SIM-617 | Correct the runtime texts that state something false | Left unedited by the clean-up's rule. (1) The park-guard messages name the deleted SIM_PARK_FACTOR: scripts/validate_props.py, scripts/accuracy_comparison.py, tests/acceptance/conftest.py and the --help of scripts/sim_stats.py. (2) The two pool rebuilds' exit-3 texts and the steal rebuild's lock message blame the app's worker server for the DuckDB lock (the app holds no handle since SIM-524), and two steal-rebuild texts say to merge code that is merged. (3) scripts/running_game_replay.py --help says a steal can land on any pitch in production. (4) Three texts point at a module docstring section that moved in the split. (5) scripts/measure_filter_cells.py writes into docs/audit/. (6) scripts/resumable_sweep.py --help cites a deleted record. (7) The rationale strings in tests/acceptance/bands.py cite BACKLOG.md, which is gone. Found by the code clean-up (SIM-493, B5 scripts and test harness, 2026-10-20); the evidence is in its CHANGES.md entry. | Each text says what is true. | One edit per text; list the runtime-string changes in CHANGES.md.
P3 | SIM-618 | Keep one copy of the prop ground-truth readers | scripts/validate_props.py and scripts/accuracy/grading.py each define _fetch_official_boxscore and _fetch_pa_events. Found by the code clean-up (SIM-493, B5 scripts and test harness, 2026-10-20); the evidence is in its CHANGES.md entry. | One reader, imported by both. | Move it to simulation/prop_validation.py.
P3 | SIM-619 | Run the batch-runner stress test in a CI job | tests/integration/test_batch_runner_stress.py carries only the slow marker. The CI slow lane runs tests/unit -m slow; the weekly integration lane and make test-integration select -m integration; the e2e job runs one file. No job runs it. Found by the code clean-up (SIM-493, B5 scripts and test harness, 2026-10-20); the evidence is in its CHANGES.md entry. | One lane runs it. | Mark it integration, or add its path to the slow lane.
P3 | SIM-620 | Delete the regression gate's dead constants and its golden-file texts | tests/regression/regression_config.py: only SYMMETRY_TOLERANCE has a reader; eight constants have none (the conftest hard-codes the seed 2026). The assert message in test_engine_regression.py and the regression marker text in pyproject.toml name golden files the gate does not have. Found by the code clean-up (SIM-493, B5 scripts and test harness, 2026-10-20); the evidence is in its CHANGES.md entry. | The dead constants go, and the texts say what the gate checks. | Delete them and edit the two texts.
P3 | SIM-621 | Bench the per-pitch call the loop makes | tests/performance/bench_simulation.py times PitcherSimilarityEngine.query() as the per-pitch cost; the loop reads the dense pitcher matrix. bench_api_simulate.py says an authoritative gate runs on target hardware with the DB-backed factory; no job does. Found by the code clean-up (SIM-493, B5 scripts and test harness, 2026-10-20); the evidence is in its CHANGES.md entry. | The benches time what the loop runs, and the SLA text names the job that gates it. | Bench the matrix read; correct the SLA text.
P3 | SIM-622 | Use the pinned park factor in the sim-kwargs tests | tests/unit/test_sim_kwargs.py uses 0.8723846078 for venue 680 in six places; the pinned 2024 table in the same file holds 0.8725842237. The tests pass (the literal is only an input). Found by the code clean-up (SIM-493, B5 scripts and test harness, 2026-10-20); the evidence is in its CHANGES.md entry. | One value. | Read it from the table.
P3 | SIM-623 | Replace the inning-grid test's pinned scores with an outcome check | tests/unit/test_inning_grid.py pins the exact scores and pitch counts of ten seeds (OUTCOMES_AT_80E3F46). That works like the golden snapshots the owner ruled out on 2026-09-10: any intended change to the draw fails it. Found by the code clean-up (SIM-493, B1 simulation, 2026-10-20); the evidence is in its CHANGES.md entry. | The test checks a property of the grid (its sum equals the final score, the halves match the outs), not ten remembered numbers. | Rewrite the assertions as invariants and delete the pinned table.
Priority key: | P0 — immediate | P1 — next up | P2 — planned | P3 — later